# COMMUNITY LINK PROJECT CONTRACT

| Contractor’s Name: Dale Carnegie | Client’s Name: Harry Styles |
| --- | --- |
| Address: 123 Example Street Syracuse, NY 13244 | Address: 456 Sample Avenue Syracuse, NY 13210 |
| Phone: (315)-123-4567 | Phone: (315)-123-5678 Fax: (315)-123-9012 |
| Email: dcarnegie@example.com | Email: hstyles@example.com |

Brief Description of the Project: One Direction Fan Club Satisfaction Survey

The Contractor agrees to conduct the following research and development activities*:

1. Prepare a web-based survey with Mr. Styles to administer to the One Direction Fan Club (5,000 members)

2. Input responses from Fan Club members

3. Prepare (at least) seven graphs visualizing data

4. Email bi-weekly progress reports

The Contractor will deliver the following to the Client by: 4/14/2023

1. A Final Report in Word and PDF format

2. Excel file with data and codebook

3. Presentation to be presented via Zoom to One Direction by 5/1

The contractor expects to spend 90 hours in order to complete this project.

The Client agrees to provide the following support:

| 1. Background information about the One Direction Fan Club | By: 02/8/2023 |
| --- | --- |
| 2. Email list for One Direction Fan Club members | By: 02/8/2023 |
| 3. Responses to requests for information within 48 hours | By: Ongoing |

This agreement is entered into on: 01/25/2023 by:

# Contractor 		 				Client

Signed: _Dale Carnegie________________		Signed: __

Print: 	Dale Carnegie					Print: Harry Styles

Project Timeline

Add rows for additional tasks if needed. Notes should be used to detail specific expectations that should be met for each task.

| Task | Deadline | Notes |
| --- | --- | --- |
| Contract and Timeline Finalized | 1/25/2023 |  |
| Second Client Meeting | 2/1/2023 | Meeting is over Zoom. Mr. Carnegie will email Mr. Styles the link to the meeting no later than 24 hours before. |
| Finalize Survey Design (if applicable) | 2/17/2023 | First draft of survey design to take place during second meeting. After edits, Mr. Carnegie will email the design to Mr. Styles for approval. |
| Begin data collection (if applicable) | 2/20/2023 | After final survey design is approved, Mr. Carnegie will input the data into an Excel spreadsheet and distribute the file via the supplied email list. |
| Finish data collection (if applicable) | 3/10/2023 | Once survey is sent out, the survey will remain open for three weeks with a reminder being sent to Fan Club members who have not answered every 3-5 days. |
| Update Timeline (if necessary) | Ongoing |  |
| Data received (or entered) by Contractor in an Excel Spreadsheet | 3/29/2023 | The data will be entered by submission of draft. |
| Rough draft | 3/29/2023 | Draft will be emailed to client by 2:15 PM. |
| Final report | 4/14/2023 | Report will be emailed to client by 5:00 PM. |
| Presentation for client (if applicable) | TBD |  |